# Invoice

Invoice ID: INV-2026-5017 Contract ID: CTR-2026-0055 Supplier: Vantage Point Consulting Group LLC Tax ID: 45-8812093 Invoice Date: 2026-05-31 Due Date: 2026-06-30 (Net 30) Billing Period: May 2026 (Design Phase, Month 4 of 6)

## Summary

This invoice covers Design Phase professional services and pre-approved travel expenses for May 2026, per the monthly percentage-of-completion billing structure defined in Section 3.1 of the Master Services Agreement.

## Professional Services

| Line Item | Role | Hours | Rate | Amount |
| --- | --- | --- | --- | --- |
| Process reengineering workshops (3 sessions) | Engagement Lead | 24 | $385/hr | $9,240.00 |
| Future-state design documentation | Program Manager | 40 | $265/hr | $10,600.00 |
| Stakeholder interviews (Finance dept.) | Senior Consultant | 32 | $225/hr | $7,200.00 |
| Technology roadmap drafting | Senior Consultant | 28 | $225/hr | $6,300.00 |
| Change management planning | Change Management Lead | 20 | $250/hr | $5,000.00 |
| Weekly status reporting and governance calls | Program Manager | 8 | $265/hr | $2,120.00 |
| Professional Services Subtotal |  |  |  | $40,460.00 |

Note: Contracted Design Phase monthly fee under Section 3.1 is $58,333.33; this invoice reflects $40,460.00 in services because two planned stakeholder interview sessions were rescheduled to June at the Company’s request. The remaining balance will be reflected in next month’s invoice per the percentage-of-completion methodology, not carried forward as an overage.

## Expense Reimbursement

| Item | Description | Amount |
| --- | --- | --- |
| Travel — Engagement Lead | Round-trip flight + 2 nights hotel, on-site workshop (May 12-13) | $1,840.00 |
| Travel — Program Manager | Round-trip flight, on-site workshop (May 12) | $620.00 |
| Ground transportation | Client-site visits, May 12-13 | $215.00 |
| Expense Subtotal |  | $2,675.00 |

Expense cap check: $2,675.00 represents 6.6% of this month’s professional services fee, within the 8% cap defined in MSA Section 3.3.

## Invoice Total

Professional Services: $40,460.00 Expenses: $2,675.00 Total Invoiced Amount: $43,135.00

## Deliverables Referenced This Period

- Future-state process design documentation (in progress, 60% complete)

- Stakeholder interview summary — Finance department (attached)

- Technology roadmap draft v0.3 (attached)

## Supporting Notes

This is the fourth invoice under this Agreement. Cumulative Design Phase payments to date (including this invoice): $157,940.00 against a Design Phase allocation of $350,000.00, well within the phase budget defined in MSA Section 3.1.

Reviewer note: this invoice is below the expected monthly run-rate due to a Company-requested schedule change, not a billing discrepancy — flag as Pass with an explanatory note rather than a Warning for schedule deviation, per the context provided above. Expense ratio is within the contracted cap.